Guide2. Desarrollo Proyecto APT

Asignatura Capstone

1. APT Project Progress Summary

Below, you will find various fields that you should complete with the requested information.

| APT Project Progress Summary | Sprint 1 Summary – APT Project Completed Tasks: - Web development: main pages implemented. - User CRUD: functional. - Reports and transactions: functionalities ready. - Role management: implemented. - Database integration: modules interact correctly with data and historical loads. Tasks in Progress or Pending: - Alert system: pending stabilization. - Password recovery: pending implementation. Delayed Tasks: - Training with Llama 2 AI: not yet started. - Predictions: inclusion of graphs with predictions will depend on AI training. Database and Data Analysis: - Transaction model: under development using MariaDB; integration with BigQuery is pending evaluation. - Data analysis: started using the data behavior template. |
| --- | --- |
| Objectives | No changes have occurred |
| Methodology | No changes have occurred |
| Progress Evidence | 1. Reflection Journal – Phase 2: Records learning, decisions made, and problem-solving during the progress phase. 2. Progress Report: Supports project tracking and the achievement of the specific objectives of this phase. 3. System Flowchart: Demonstrates the design and logic of processes, facilitating understanding of the system’s structure. 4. Software in Development: Shows the technical and functional progress of the project, evidencing the implemented functionalities. (GitHub) |

2. Work Plan Monitoring

Carefully review your work plan, focusing especially on the progress status and adjustments column.

| Work Plan APT Project |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or Units of Competencies | Activities/Tasks | Resources | Duration of Activity | Responsible | Observations | Progress Status | Adjustments |
| -Requirements gathering and analysis -Problem solving -Teamwork | Requirements gathering | - 2× Computers- Office 365 | 2 weeks | Maikel Cisternas | Minor delays due to client consultation on profitable project | Completed | No adjustments needed |
| -IT project management -Teamwork | Sprint planning | - 2× Computers- Office 365 | 1 week | Marcelo Peña | Initial delays due to Phase 1 review | Completed | Minor timing adjustment due to first delay |
| - System development, adaptation, and/or integration | Web development | - 2× Computers- Django | 1 week | Maikel Cisternas | Alerts and predictive graphs pending | Completed | Task redistribution; complex tasks broken down |
| - System development, adaptation, and/or integration | Database development | - 2× Computers- MariaDB- BigQuery | 1 week | Maikel Cisternas | Transaction model worked in MariaDB for now | Completed | Working with MariaDB for the moment |
| -Information management | Data analysis development | - 2× Computers | 3 weeks | Marcelo Peña | Late start due to dependency on data template received late | Completed | Work analysis together with AI training |
| -System development, adaptation, and/or integration -Teamwork | System integration development | - 2× Computers- Google Cloud Platform | 2 weeks | Maikel Cisternas | Partial integration; delays generating simulated data | Completed | Prioritize integration with simpler technologies |
| -Requirements gathering and analysis -Software quality assurance -Problem solving | Review and feedback | - Computer- Projector | 1 week | Maikel Cisternas | Done on incomplete tasks | Completed | Done partially; will be revisited after AI integration |
| -Technological solutions development | AI training | - 2× Computers- Llama 2 | 1 week | Marcelo Peña | Not yet started; depends on data generation and final database structure | Not started | Will start in week 10 |
| -Information technology integration | AI integration | - 2× Computers- Llama 2 | 1 week | Maikel Cisternas | — | Not started | — |
| -Software quality assurance | AI interaction testing | - 2× Computers- Office 365- Llama 2 | 1 week | Marcelo Peña | — | Not started | — |
| -Requirements gathering and analysis -Software quality assurance -Problem solving | Review and feedback | - Computer- Projector | 1 week | Maikel Cisternas | — | Not started | — |
| -Computer systems security | Platform security testing | - 2× Computers- Security testing tools (e.g., OWASP ZAP, basic encryption tools) | 1 week | Maikel Cisternas | — | Not started | — |
| -Software quality assurance -Teamwork | Quality and usability testing | - 2× Computers- Office 365 | 1 week | Marcelo Peña | — | Not started | — |
| -IT project management -Teamwork | Technical documentation | - 2× Computers- Office 365 | 2 weeks | Maikel Cisternas | — | Not started | — |
| -Requirements gathering and analysis -Software quality assurance -Problem solving | Review and feedback | - Computer- Projector | 1 week | Maikel Cisternas | — | Not started | — |
| -Problem solving -Teamwork | Presentation to committee | - Computer- Projector- Office 365 | 1 week | Maikel Cisternas and Marcelo Peña | — | Not started | — |
| -Problem solving | Individual APT project presentation to committee | - Computer- Projector- Office 365 | 2 weeks | Maikel Cisternas and Marcelo Peña | — | Not started | — |

3. Adjustments Based on Monitoring

Delve into the observations from your work plan. Analyze the planned activities and identify which aspects facilitated or hindered the execution of the plan. Explain how you addressed and/or plan to address the obstacles. Finally, indicate the adjustments you made to the work plan based on this analysis.

Factors That Have Facilitated and/or Hindered the Development of My Work Plan: The project started with approximately a two-week delay, plus a couple of additional days due to holidays. Factors that facilitated development include the reuse of code from previous projects with similar contexts, correcting deficiencies and errors. The difficulties include: - The first week of the schedule was dedicated to testing Phase 1 (presentation + report). - The first meeting with the client to request the cost report template was delayed by a week, affecting the simulation of sales, expenses, and payroll data. - Changes in the defined technologies during development caused delays and difficulties in implementing ideas. To address these difficulties, priority was given to working with the initially defined technologies, maintaining constant communication among team members, and ensuring the proper transmission of client information to progress efficiently.

Adjusted or Removed Activities: The participation of one team member in the web development was adjusted, involving them more actively so that progress would be reflected in GitHub commits. This adjustment was not due to technical difficulties, but because the person in charge encountered problems implementing other equally or more efficient technologies that they did not fully master. Additionally, the member who was initially integrated had not been able to work much due to the lack of simulated data (the client’s template was required). The redistribution of tasks allowed for a more balanced workload, and some activities were broken down or partitioned to improve execution and clarity.

Activities Not Started or Delayed: The delayed activities include: - Web development (the alert system functionality and predictive graphs still need to be implemented). - Database (currently working only with MariaDB). - Data analysis (recently started with the behavior data template, so it can be improved). Activity not started: - Llama 2 AI modules, which were expected to begin training in week 9. The delays are due to the underestimated complexity of some tasks and external issues, such as the initial lack of the client’s report template. To move forward, the plan is to divide large tasks into manageable sub-tasks, assign more realistic timeframes, and maintain constant communication among team members, ensuring the project progresses without affecting the deadlines for the second delivery.